## Milestone
[5 empty] | 2018 |  |  |  | 2019
Milestone | INT | QA | UAT | Prod | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
1st - Build Centralize Eligibility Database:
Identify eligibility related tables, indexes, displays and programs | 16 | 16 | 16 | 20 | l | l
Modernize Eligibility database (convert decimal Date/Time with true Date/Time) |  |  |  |  | l
Enhance carrier or carrier extension table to include "Instance ID" | 10 | 10 | 20 | 40 | l
Identify and partition large tables like MEL, AMD, etc. | 4 | 4 | 4 | 8 | l
Convert roll logic to SQL triggers that move inactive records to history tables | 250 | 250 | 250 | 400 | l
Build lower [SYS/INT, QA & UAT] environments:
IBM i Partition [re purpose existing partition - RxMCMTST] | [5 empty] | l
Webspher/App/Cloud Servers | [5 empty] | l
Install MQ/MQFTE to support BK2 NRT | [5 empty] | l
Build connectivity for PEER, ERA, Ab Initio, sterling integrator, etc. | 4 | 4 | 4 | 4 |  | l | l
Build MIMIX Share AKA Double-Take data replication model from centralized eligibility to respective RxCLAIM instances | [5 empty] | l
Build Web Service that replicate dynamic enrolment changes from all RxCLAIM instances to centralized eligibility | [5 empty] | l | l
Build data compare utility or Audit data between RxCLAIM instances and Centralize eligibility | 4 | 4 | 4 | 8 |  | l | l
Convert RxCLAIM eligibility screens to read-only | 16 | 16 | 16 | 16 |  | l | l
Production Deployment / Roll-out
Build production environment | [7 empty] | l
IBM i Partition | [7 empty] | l
Webspher/App/Cloud Servers | [7 empty] | l
Install MQ/MQFTE to support BK2 NRT | [7 empty] | l
Build connectivity for PEER, ERA, Ab Initio, sterling integrator, etc. | 4 | 4 | 4 | 4 |  |  |  | l
Perform Performance Testing
Eligibility Stage/Load | [7 empty] | l
MIMIX Share data replication | [7 empty] | l
Web/GUI application | [7 empty] | l
Data migration strategy and migrate historical data from all RxCLAIM instances to Centralize eligibility | 80 | 80 | 80 | 80 |  |  |  | l | l | l
Install, configure & schedule Stage/Load process for Member & Group Eligibility | [7 empty] | l | l | l
Configure MIMIX Share data replication model | [7 empty] | l | l | l
Install, configure & schedule data compare utility / audit data between all RxCLAIM instances and centralize eligibility | [7 empty] | l | l | l
Convert RxCLAIM eligibility screens to read-only to all RxCLAIM instacnes | [8 empty] | l | l
Role out solution to all RxCLAIM instances (13+), Post Production go-live monitoring and Support |  |  |  | 800 |  |  |  |  | l | l
2nd - Design & Build Web GUI
Design & Build Web base interface/GUI application | [5 empty] | l | l | l
Design & Build security framework | [5 empty] | l | l | l
Define roles in Optum ID, tied to GUI page access | [6 empty] | l | l
Define client in Optum ID, tied to row-level access (eliminate the use of client logical views) | [6 empty] | l | l
Protect SSN been displaying on GUI page | [6 empty] | l | l
Build centralize dash board (end to end process view) to get incoming file status, pend, in process, complete, etc. | 4 | 4 | 4 | 4 |  |  | l | l
Production Deployment / Roll-out
Deploy / roll-out Web GUI | [8 empty] | l
Configure user/client access as solution roll-out to each RxCLAIM instances | [8 empty] | l | l
3rd - Web Service/API
Build Microservices (Web Service/API) for eligibility & claim lookups | [7 empty] | l
Repoint all external API/Web Service which is to start consuming Centralize Eligibility Data | [7 empty] | l
Production Deployment / Roll-out
Deploy / roll-out solution | [9 empty] | l
Deprecate RxCLAIM eligibility screens | [9 empty] | l

## Resources (hidden)
PROJECT PLANNING TEMPLATE |  |  |  |  | Total Resource Hours 2016 | 6120 | [78 empty] | SPRF # | Description | Target Deploy | Role | UHC Area (if not ORx) |  | ApplicationName
2016-07-29 |  |  |  |  | 2016 Q4 Forecasted Hours | 1344 | [78 empty] | 70939 | 70939 iHOP | 2015 Q1 | App PM | UHC - C&S | 1 | CSQA
[5 empty] | 2016 Q4 Forecasted Hours | 3928 | [78 empty] | 70940 | 70940 Performance Test | 2015 Q2 | Cross App PM | UHC - E&I | 2 | Consumer Portal (ORx)
[5 empty] | 2017 Q1 Forecasted Hours | 848 | [80 empty] | 2015 Q3 | Dev | UHC - M&R | 3 | Eligibility Reformat Automation (ERA)
[5 empty] | 2017 Q2 Forecasted Hours | [81 empty] | 2015 Q4 | Dev-Mgmt | ORx | 4 | IRIS
[87 empty] | 2016 Q1 | oCIO PM | OT | 5 | ORx CCR (Central Client Repository)
Project Name: |  | 99999 xxxxxxxx | [84 empty] | 2016 Q2 | SA |  | 6 | ORx IT QA and Process Improvement
[7 empty] | 2015-01-01 | [5 empty] | 2015-02-01 |  |  |  |  | 2015-03-01 |  |  |  |  | 2015-04-01 |  |  |  |  | 2015-05-01 | [5 empty] | 2015-06-01 |  |  |  |  | 2015-07-01 | [5 empty] | 2016-08-01 |  |  |  |  | 2016-09-01 | [5 empty] | 2016-10-01 |  |  |  |  | 2016-11-01 |  |  |  |  | 2016-12-01 | [5 empty] | 2017-01-01 |  |  |  |  | 2017-02-01 | [9 empty] | 2016 Q3 | SA-Mgmt |  | 7 | ORx Online Reporting
Resource | non-ORx | Role | Target Deploy | SPRF# | Description | Application Name | 2015-01-02 | 2015-01-09 | 2015-01-16 | 2015-01-23 | 2015-01-30 |  | 2015-02-06 | 2015-02-13 | 2015-02-20 | 2015-02-27 | Feb | 2015-03-06 | 2015-03-13 | 2015-03-20 | 2015-03-27 | Mar | 2015-04-03 | 2015-04-10 | 2015-04-17 | 2015-04-24 | Apr | 2015-05-01 | 2015-05-08 | 2015-05-15 | 2015-05-22 | 2015-05-29 | May | 2015-06-05 | 2015-06-12 | 2015-06-19 | 2015-06-26 | Jun | 2015-07-03 | 2015-07-10 | 2015-07-17 | 2015-07-24 | 2015-07-31 | Jul | 2015-08-05 | 2015-08-12 | 2015-08-19 | 2015-08-26 | Aug | 2015-09-02 | 2015-09-09 | 2015-09-16 | 2015-09-23 | 2015-09-30 | Sep | 2015-10-07 | 2015-10-14 | 2015-10-21 | 2015-10-28 | Oct | 2015-11-04 | 2015-11-11 | 2015-11-18 | 2015-11-25 | Nov | 2015-12-02 | 2015-12-09 | 2015-12-16 | 2015-12-23 | 2015-12-30 | Dec | 2016-01-06 | 2016-01-13 | 2016-01-20 | 2016-01-27 | Jan | 2016-02-03 | 2016-02-10 | 2016-02-17 | 2016-02-24 | Feb | [5 empty] | 2016 Q4 | Dev-Lead |  | 8 | ORx RxHD
| Area | [85 empty] | 2017 Q1 |  |  | 9 | ORx WebServices
Total Hours | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 120 | 120 | 280 | 280 | 224 | 280 | 280 | 280 | 1064 | 320 | 320 | 320 | 320 | 1280 | 320 | 320 | 320 | 192 | 1152 | 320 | 320 | 320 | 320 | 256 | 1496 | 160 | 160 | 128 | 160 | 608 | 60 | 60 | 60 | 60 | 240 |  |  | Dev Tot |  |  | 2018 Q1 |  |  | 10 | PPRM
Actual Hours to Date | [5 empty] | PPRM | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0 | [7 empty] | 11 | Prior Authorization System (PAS)
Actual Hours to Date | [5 empty] | RxCLAIM | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0 | [7 empty] | 12 | Processing Eligibility Enhancement Resource (PEER)
Actual Hours to Date | [5 empty] | Segment Architecture Services | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0 | [7 empty] | 13 | Real-Time Audit (RTA)
Actual Hours to Date | [5 empty] | ORx Online Reporting | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0 | [7 empty] | 14 | Rx Directives
Actual Hours to Date | [5 empty] | RxMAX-O© | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0 | [7 empty] | 15 | RxCLAIM
Actual Hours to Date | [5 empty] | ORx IT QA and Process Improvement | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0 | [7 empty] | 16 | RxConnection
Actual Hours to Date | [5 empty] | TOPS | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0 | [7 empty] | 17 | RxConstruct
Actual Hours to Date | [5 empty] | Prior Authorization System (PAS) | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0 | [7 empty] | 18 | RxFTS
Actual Hours to Date | [5 empty] | UM Criteria Management | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0 | [7 empty] | 19 | RxMacro
Actual Hours to Date | [5 empty] | CSQA | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0 | [7 empty] | 20 | RxMAX-O©
Actual Hours to Date | [5 empty] | ORx CCR (Central Client Repository) | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0 | [7 empty] | 21 | Segment Architecture Services
Actual Hours to Date | [5 empty] | RxConstruct | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0 | [7 empty] | 22 | UM Criteria Management
Actual Hours to Date | [5 empty] | RxMacro | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0 | [7 empty] | 23 | Vitria
Actual Hours to Date | [5 empty] | Processing Eligibility Enhancement Resource (PEER) | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0 | [7 empty] | 24 | Double-Take
Actual Hours to Date | [5 empty] | Eligibility Reformat Automation (ERA) | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0 | [7 empty] | 25 | CoD Replacement
Actual Hours to Date | [5 empty] | Vitria | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0 | [7 empty] | 26 | xCCS - Self Directed Service App (IVR)
Actual Hours to Date | [5 empty] | Rx Directives | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0 | [7 empty] | 27 | xClaims QA
Actual Hours to Date | [5 empty] | RxFTS | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0 | [7 empty] | 28 | xClient Portal
Actual Hours to Date | [5 empty] | ORx WebServices | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0 | [7 empty] | 29 | xConsumer Account Management System (CAMS)
Actual Hours to Date | [5 empty] | IRIS | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0 | [7 empty] | 30 | xIntegrated Service Experience Tool (ISET)
TBD |  | Dev-Lead |  |  | 100% | RxCLAIM | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 | 20 | 20 | 40 | 40 | 120 | 40 | 32 | 40 | 40 | 40 | 152 | 40 | 40 | 40 | 40 | 160 | 40 | 40 | 40 | 24 | 144 | 40 | 40 | 40 | 40 | 32 | 192 | 40 | 40 | 32 | 40 | 152 | 20 | 20 | 20 | 20 | 80 | 1000 | [7 empty] | 32 | xTOPS
SA1 |  | SA |  |  | 100% | RxCLAIM | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 40 | 40 | 80 | 40 | 32 | 40 | 40 | 40 | 152 | 40 | 40 | 40 | 40 | 160 | 40 | 40 | 40 | 24 | 144 | 40 | 40 | 40 | 40 | 32 | 192 | 40 | 40 | 32 | 40 | 152 | 0 | 0 | 0 | 0 | 0 | 880 | [7 empty] | 31 | xMember Interaction and Issues Mgmt Navigation
DEV-1 |  | Dev |  |  | 100% | RxCLAIM | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 40 | 40 | 80 | 40 | 32 | 40 | 40 | 40 | 152 | 40 | 40 | 40 | 40 | 160 | 40 | 40 | 40 | 24 | 144 | 40 | 40 | 40 | 40 | 32 | 192 | 40 | 40 | 32 | 40 | 152 | 20 | 20 | 20 | 20 | 80 | 960
DEV-2 |  | Dev |  |  | 100% | RxCLAIM | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 32 | 40 | 40 | 40 | 152 | 40 | 40 | 40 | 40 | 160 | 40 | 40 | 40 | 24 | 144 | 40 | 40 | 40 | 40 | 32 | 192 | 40 | 40 | 32 | 40 | 152 | 20 | 20 | 20 | 20 | 80 | 880
DEV-3 |  | DEV |  |  | 100% | RxCLAIM | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 32 | 40 | 40 | 40 | 152 | 40 | 40 | 40 | 40 | 160 | 40 | 40 | 40 | 24 | 144 | 40 | 40 | 40 | 40 | 32 | 192 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 648
DEV-4 |  | Dev |  |  | 100% | RxCLAIM | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 32 | 40 | 40 | 40 | 152 | 40 | 40 | 40 | 40 | 160 | 40 | 40 | 40 | 24 | 144 | 40 | 40 | 40 | 40 | 32 | 192 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 648
DEV-5 |  | Dev |  |  | 100% | RxCLAIM | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 32 | 40 | 40 | 40 | 152 | 40 | 40 | 40 | 40 | 160 | 40 | 40 | 40 | 24 | 144 | 40 | 40 | 40 | 40 | 32 | 192 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 648
DEV-6 |  | Dev |  |  | 100% | RxCLAIM | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 40 | 40 | 160 | 40 | 40 | 40 | 24 | 144 | 40 | 40 | 40 | 40 | 32 | 152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 456
Total - RxCLAIM | [32 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 | 20 | 20 | 120 | 120 | 280 | 280 | 224 | 280 | 280 | 280 | 1064 | 320 | 320 | 320 | 320 | 1280 | 320 | 320 | 320 | 192 | 1152 | 320 | 320 | 320 | 320 | 256 | 1496 | 160 | 160 | 128 | 160 | 608 | 60 | 60 | 60 | 60 | 240 | 6120
Nagaraja, Arcot |  | Dev |  |  | 100% | ORx WebServices | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
N, Santosh |  | Dev |  |  | 10% | Double-Take | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
Ozer, Ilhan |  | SA |  |  | 75% | RxFTS | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
Shahabudeen, Sheik |  | SA |  |  | 50% | ORx WebServices | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
Balasubramanian, Sundar |  | Dev |  |  | 10% | Processing Eligibility Enhancement Resource (PEER) | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
Total - WebServices/RxFTS | [32 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [16 empty] | 0 | +
Total | [32 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 | [38 empty] | +
Alam, Rashid |  | Dev |  |  | 10% | RxMAX-O© | [26 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [16 empty] | 0
Pauparapattykabilan, Ramanathan |  | Dev |  |  | 25% | RxMAX-O© | [5 empty] | 0 | [20 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [16 empty] | 0
Gopavarapu, Venkatasivaprasad |  | Dev |  |  | 50% | RxMAX-O© | [5 empty] | 0 | [20 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [16 empty] | 0
TBD1 |  |  |  |  | 0% | RxCLAIM | [26 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0
TBD2 |  |  |  |  | 0% | RxCLAIM | [26 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0
TBD3 |  |  |  |  | 0% | RxCLAIM | [26 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0
Senegal, Joseph |  | Dev |  |  |  | RxMAX-O© | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
Total - RxMax | [32 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [16 empty] | 0 | +
Alam, Rashid |  | Dev |  |  | 50% | CoD Replacement | [26 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [16 empty] | 0
S, Selvamuthukumar |  | SA |  |  | 25% | CoD Replacement | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
Pauparapattykabilan, Ramanathan |  | Dev |  |  | 50% | CoD Replacement | [5 empty] | 0 | [20 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [16 empty] | 0
Ramasamy, Mohanraj |  | Dev |  |  | 50% | CoD Replacement | [5 empty] | 0 | [20 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [16 empty] | 0
Ajit, Daislin |  | Dev |  |  | 100% | CoD Replacement | [5 empty] | 0 | [20 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [16 empty] | 0
Nagaraja, Arcot |  | Dev |  |  | 50% | CoD Replacement | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
N, Santosh |  | Dev |  |  | 10% | CoD Replacement | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
Ozer, Ilhan |  | SA |  |  | 50% | CoD Replacement | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
Shindich, Alina |  | Dev | [9 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
Soni, Savdesh |  | Dev | [9 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
Sreeram, Kalyana |  | Dev-Mgmt | [9 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
Tsao, Lilian |  | Dev | [9 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
Tuler, Barry |  | SA | [9 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
Werlein, Judy |  | SA-Mgmt | [9 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
xAndrade, Luis |  | Cross App PM |  | 70939 | 70939 iHOP | PPRM | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
xCarruth, Nancy+Dawn Schafer |  | App PM |  | 70939 | 70939 iHOP | PPRM | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
xKoslosky, Chris |  | oCIO PM |  | 70939 | 70939 iHOP | PPRM | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
xSilva, Norma |  | Cross App PM |  | 70939 | 70939 iHOP | PPRM | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
xWong, Vicki |  | App PM |  | 70939 | 70939 iHOP | PPRM | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
Abdou, Tarek |  | Dev-Mgmt | [9 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
Alderson, Lawrence |  | Dev-Mgmt | [9 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
Chao, Ching-Po |  | SA | [9 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
Chinnaraj, Sivasakthi |  | Dev | [9 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
Daulaghar, Harish |  | Dev | [9 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
D'Cruz, Ryan |  | Dev | [9 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
Diddee, Sameer |  | Dev-Mgmt | [9 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
Edwin, Ajithkumar |  | Dev | [9 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
Gopi, Jangala |  | Dev | [9 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
Homan, Victor |  | SA-Mgmt | [9 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
Hsu, Penny |  | Dev-Mgmt | [9 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
Jain, Navin |  | Dev-Mgmt | [9 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
Mendoza, Alex |  | Dev-Mgmt | [9 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
Narsipuram, Praveen |  | Dev | [9 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
Oh, Chuck |  | Dev | [9 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
Pedroza, Dan |  | Dev-Mgmt | [9 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
Sayaraman, Srivathsan |  | Dev | [9 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
Selvakumar, Gopal |  | Dev | [14 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
[17 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
[17 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
[17 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
[17 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0