## User Stories
Backlog Quality Assessment Reference for User Stories
Scoring
Score | Criteria |  |  | Next Steps
1 | The user story exists as a mere placeholder with no level of detail or quality |  |  | Team continues to work to refine the user story
2 | Some of the questions have "yes" answers |  |  | Team continues to work to refine the user story
3 | Team has reviewed every category - each has at least one "yes" answer |  |  | Focus on the criteria for all of the required questions
4 | Team has reviewed every category - each has at least one "yes" answer and all required questions have a "yes" answer |  |  | Required score to pass quality inspection and to allow sizing exercises to occur
5 | Team fully meets all quality requirements and chooses to provide additional components to the user story for development purposes
Assessment Questions
Category |  | Type | Question |  | Answer | INVEST
Consistent |  | Required | Is the user story independent— its requirements do not overlap with those in other user stories? |  |  | I - Independent
|  | Required | Is the user story negotiable, so that it ultimately reflects shared meaning and goals? |  |  | N - Negotiable
|  | Suggested | Is the user story free of conflict with the requirements in other user stories?
|  | Required* | (*Required for Scaled Agile projects) Does the user story trace up to a feature and a solution capability without conflict or deviation from concepts stated in those parent levels?
Clear |  | Required | Does the user story identify the Who, What, and Why elements? |  |  | V - Value
|  | Required | Does the user story have acceptance criteria? |  |  | E - Estimable
|  | Suggested | Is the user story written using plain, common language without ambiguous terms? | Is the User Story written using plain, common language and there are no ambiguous terms?
|  | Suggested | Does the user story clearly bring business value and isn't a task? | Does the User Story clearly bring business value and isn't a "task"?
Concise |  | Required | Is the user story is small enough to be sized appropriately to fit within a sprint? | Is the User Story is small enough to be sized appropriately to fit within a Sprint? |  | S - Small
|  | Suggested | Does the user story remain focused on a core concept and not contain extra information that is unrelated to the core concept? | Does the User Story remain focused on a core concept and not contain extra information that is unrelated to the core concept?
|  | Suggested | Does the user story avoid redundancy within itself? | Does the User Story avoid redundancy within itself?
|  | Suggested | Does the user story contain specific ideas, rather than generalizations? | Does the User Story contain specific ideas, rather than generalizations?
Complete |  | Required | Are all business rules, calculations, and detailed logic clearly stated somewhere in support of the user story, with no missing critical information? | Are all business rules, calculations, and detailed logic clearly stated somewhere in support of the User Story, with no missing critical information? |  | T - Testable
|  | Suggested | Are all applicable conditions and business scenarios accounted for? | Are there all applicable conditions and business scenarios accounted for?
|  | Suggested | Are nonfunctional requirements included in the acceptance criteria or written as separate nonfunctional user stories? | Are nonfunctional requirements included in the acceptance criteria or written as seperate nonfunctional User Stories?
|  | Suggested | Does it identify the "before" to "after" state clearly? | Does it identify the "before" to "after" state clearly?
Concrete |  | Suggested | Does the user story list clear and properly sequenced process steps, where warranted? | Does the User Story list clear and properly sequenced process steps, where warranted?
|  | Suggested | Are dependencies with external factors clearly stated? | Are dependencies with external factors clearly stated?
|  | Suggested | Are dependencies with other interfaces and / or applications clearly stated? | Are dependencies with other interfaces and / or applications clearly stated?
|  | Suggested | Are impacts to the system, data flow, or work flow clear? | Are impacts to the system, data flow, or work flow clear?